## Written out planning
Main goals	Sub goals	Time needed actual time	Time needed in working time	When starting	When finishing
Making MA available for everybody
	Interview everybody involved in testing about how much time they spent on both manual and automatic testing	3 days	2.25 weeks	2018-06-06	2018-07-06
	Determine how to calculate MA	3 days	2.25 weeks	2018-07-06	2018-07-24
	Perform tests manually and automatically and keep track of time spent to check repeatability factor	5 days	3.75 weeks	2018-07-24	2018-09-01	Includes 1 week holiday
	React app (??????) showing the actual Repeatability factor	1 day	2 week	2018-09-01	2018-09-15
Improve the MA. 80% of all the tests performed before mergin a branch in Xillio will be automatically tested
	Inventorize all kinds of tests that need manual testing	½ day	1 week	2018-09-15	2018-09-22
	Determine all kind of tests that can be automatically tests	½ day	1 week	2018-10-22	2018-10-29
Having performance testing running on a nightly basis
	Create a simple performance test in Jmeter for Xillio Engine	2 days	1 ½ week	2018-10-29	2018-11-09
	Run the Jmeter performance test in Jenkins + repeat the test every night	1 day	¾ week	2018-11-09	2018-11-13
	Push result of Jmeter performance to React app (?????)	2 days	1 ½ week	2018-11-13	2018-11-23

## GANTT
Main goal	Sub goal		W24: 11-06/17-06	W25: 18-06/24-06	W26: 25-06/01-07	W27: 02-07/08-07	W28: 09-07/15-07	W29: 16-07/22-07	W30: 23-07/29-07	W31: 30-07/05-08	W32: 06-08/12-08	W33: 13-08/19-08	W34: 20-08/26-08	W35: 27-08/02-09	W36: 03-09/09-09	W37: 10-09/16-09	W38: 17-09/23-09	W39: 24-09/30-09	W40: 01-10/07-10	W41: 08-10/14-10	W42: 15-10/21-10	W43: 22-10/28-10	W44: 29-10/04-11	W45: 05-11/11-11	W46: 12-11/18-11	W47: 19-11/25-11	W48: 26-11/02-12	W49: 03-12/09-12	W50: 10-12/16-12	W51: 17-12/23-12	W52: 24-12/30-12	W53: 31-12/06-01

Making MA available for everybody
	Interview everybody involved in testing about how much time they spent on both manual and automatic testing
	Determine how to calculate MA
	Perform tests manually and automatically and keep track of time spent to check repeatability factor
	React app (??????) showing the actual Repeatability factor
Improve the MA. 80% of all the tests performed before mergin a branch in Xillio will be automatically tested
	Inventorize all kinds of tests that need manual testing
	Determine all kind of tests that can be automatically tests
Having performance testing running on a nightly basis
	Create a simple performance test in Jmeter for Xillio Engine
	Run the Jmeter performance test in Jenkins + repeat the test every night
	Push result of Jmeter performance to React app (?????)