## Written out planning
Main goals | Sub goals | Time needed actual time | Time needed in working time | When starting | When finishing
Making MA available for everybody
| Interview everybody involved in testing about how much time they spent on both manual and automatic testing | 3 days | 2.25 weeks | 2018-06-06 | 2018-07-06
| Determine how to calculate MA | 3 days | 2.25 weeks | 2018-07-06 | 2018-07-24
| Perform tests manually and automatically and keep track of time spent to check repeatability factor | 5 days | 3.75 weeks | 2018-07-24 | 2018-09-01 | Includes 1 week holiday
| React app (??????) showing the actual Repeatability factor | 1 day | 2 week | 2018-09-01 | 2018-09-15
Improve the MA. 80% of all the tests performed before mergin a branch in Xillio will be automatically tested
| Inventorize all kinds of tests that need manual testing | ½ day | 1 week | 2018-09-15 | 2018-09-22
| Determine all kind of tests that can be automatically tests | ½ day | 1 week | 2018-10-22 | 2018-10-29
Having performance testing running on a nightly basis
| Create a simple performance test in Jmeter for Xillio Engine | 2 days | 1 ½ week | 2018-10-29 | 2018-11-09
| Run the Jmeter performance test in Jenkins + repeat the test every night | 1 day | ¾ week | 2018-11-09 | 2018-11-13
| Push result of Jmeter performance to React app (?????) | 2 days | 1 ½ week | 2018-11-13 | 2018-11-23

## GANTT
Main goal | Sub goal | W24: 11-06/17-06 | W25: 18-06/24-06 | W26: 25-06/01-07 | W27: 02-07/08-07 | W28: 09-07/15-07 | W29: 16-07/22-07 | W30: 23-07/29-07 | W31: 30-07/05-08 | W32: 06-08/12-08 | W33: 13-08/19-08 | W34: 20-08/26-08 | W35: 27-08/02-09 | W36: 03-09/09-09 | W37: 10-09/16-09 | W38: 17-09/23-09 | W39: 24-09/30-09 | W40: 01-10/07-10 | W41: 08-10/14-10 | W42: 15-10/21-10 | W43: 22-10/28-10 | W44: 29-10/04-11 | W45: 05-11/11-11 | W46: 12-11/18-11 | W47: 19-11/25-11 | W48: 26-11/02-12 | W49: 03-12/09-12 | W50: 10-12/16-12 | W51: 17-12/23-12 | W52: 24-12/30-12 | W53: 31-12/06-01
Create method to get people up to speed with QA-ing at Xillio
Making MA available for everybody
Interview everybody involved in testing about how much time they spent on both manual and automatic testing
Determine how to calculate MA
Perform tests manually and automatically and keep track of time spent to check repeatability factor
React app (??????) showing the actual Repeatability factor
Improve the MA. 80% of all the tests performed before mergin a branch in Xillio will be automatically tested
Inventorize all kinds of tests that need manual testing
Determine all kind of tests that can be automatically tests
Having performance testing running on a nightly basis
Create a simple performance test in Jmeter for Xillio Engine
Run the Jmeter performance test in Jenkins + repeat the test every night
Push result of Jmeter performance to React app (?????)